## General
General Contributions
Group Member | Date(s) | Time Spent (hours) | Topic(s) | File(s) Modified | Notes
Malin | 2018-05-22 | 3 | Requirements | Requirements Google Doc & GitHub page | Product functions & UML, constraints and editing of html
Rumsha | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Helped design first draft of GUI
Navreet | 2018-05-22 | 2.5 | GUI | GUI Prototype | Helped design first draft of GUI (specifically chat interface)
Michelle | 2018-05-22 | 2 | GUI | GUI Prototype | Helped design first draft of GUI (specifically loading screen)
Christian | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Introduction
Zakaria | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Introduction - scope and definitions
Jessica | 2018-05-22 | 3 | Requirements | Requirements Google Doc | User characteristics, constraints
Samani | 2018-05-22 | 3 | Requirements | Requirements Google Doc | Product functions, constraints
Pranav | 2018-05-22 | 3 | Requirements | Requirements Google Doc | Performance requirement, Security, Portability
Kokul (Harry) | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Introduction - Definitions, Acronyms, Abbreviations, References
Tiffany | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Assumptions and Dependencies
Emily | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Overall Description and Definitions
Delina | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Introduction - Definitions, Acronyms, Abbreviations, References, assisted in user characteristics
Keats | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Overall Description and Definitions
Jared | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Worked on Introduction and description
Adam | 2018-05-22 | 2 | Requirements | Requirements Google Doc | Bluetooth Core descriptions and intro
Jared | 2018-05-22 | 1 | Requirements | Requirements Google Doc | Helped divide up team between team members
Duncan | 2018-05-22 | 2 | Requrements | Requirements Google Doc | Corrected document based on in-class discussion
Adam | 2018-06-01 | 2 | Development | IOS Repo
Emily | 2018-06-03 | 2 | Analysis | Analysis Git Hub/Google Docs | Object Classification
Delina | 2018-06-03 | 2 | Analysis | Analysis Git Hub/Google Docs | Object Classification
Jayanth | 2018-06-03 | 3 | Analysis | Analysis Git Hub/Google Docs | Object Classification
Malin | 2018-06-04 | 1 | Requirements/Analysis | Requirements GitHub page | Corrected document based on in-class discussion
Samani | 2018-06-04 | 1 | Requirements/Analysis | Requirements GitHub page | Corrected document based on in-class discussion
Jessica | 2018-06-04 | 0.5 | Requirements/Analysis | Requirements GitHub page | Corrected document based on in-class discussion
Delina | 2018-06-04 | 3 | Analysis | Analysis Git Hub/Google Docs | Object Controller Diagrams
Pranav | 2018-06-04 | 1 | Requirements | Requirements GitHub page | Corrected document based on in-class discussion
Navreet | 2018-06-04 | 0.5 | GUI | GUI Prototype/Requirements Git Hub | Added additional feature on GUI prototype from SQA
Tiffany | 2018-06-04 | 3 | Analysis | Object Oriented Analysis | Object Descriptors/Object Diagrams
Zakaria | 2018-06-04 | 2 | Analysis | Object Oriented Analysis | Object Descriptors/Object Diagrams
Cristian | 2018-06-04 | 2 | Analysis |  | Researched Bluetooth Low Energy technology to gain a better understanding of how it works
Zakaria | 2018-06-05 | 0.5 | Requirements | Requirements | Corrected part of the introduction based on in class discussion
Andrew | 2018-06-05 | 0.5 | Analysis | Object Oriented Analysis | Object Descriptors/Object Diagrams
Jessica | 2018-06-20 | 3 | GUI | GUI Prototype | Redesigned initial layouts and added settings page
Malin | 2018-06-20 | 5 | GUI | iOS Development | Installed Flutter and did tutorials (ended up not useful)
Emily | 2018-06-21 | 2 | Analysis | Analysis/GitHub | Updating UML charts and Event Loops
Malin | 2018-06-22 | 2 | GUI | iOS | Swift Tutorials online (AppCoda)
Farhan | 2018-06-24 | 3 | Design | GUI Prototype | Bubbles and stuff
Farhan | 2018-06-24 | 0.5 | Design | Design Analysis | Top level diagram
Tiffany | 2018-06-24 | 2 | Design | GUI Prototype | Chat Formatting - Bubbles
Tiffany | 2018-06-24 | 0.5 | Design | Design Analysis | Goals and Guidelines
Emily | 2018-06-24 | 3 | Design | Design Google Docs/Github | Design Considerations and Architecual Strategies
Christian | 2018-06-24 | 3 | Design | IOS Development | Learning new language Flutter
Harry | 2018-06-24 | 3 | Design | IOS Development | Download/Setup XCode, learn Swift
Navreet | 2018-06-24 | 2.5 | SPMP | Software Project Management Plan (SPMP) | Template, Introduction
Michelle | 2018-06-24 | 3 | Prototype | Github | Worked on attempted prototype
Jessica | 2018-06-24 | 3 | GUI | GUI Prototype | Added additional features on GUI prototype
Malin | 2018-06-24 | 3 | GUI | iOS Development | Tried to figure out constraints
Jared | 2018-06-24 | 3 | GUI | GUI Prototype | Began work on the Android version of the GUI
Delina | 2018-06-24 | 3 | Design | iOS Development | Flutter Research and beginning implementation
Adam | 2018-06-24 | 1.5 | Design | Design | GUI prototype work
Greg | 2018-06-24 | 10 | Development | Shout POC | Made flutter POC for shout
Ben | 2018-06-24 | 6 | Development | Shout POC | Made flutter POC for shout
Jessica | 2018-06-27 | 3 | GUI | GUI Prototype | Standardized GUI prototype to match Apple's Human Interface Guidelines, and Android prototype
Pranav | 2018-06-27 | 2 | GUI | GUI Prototype | Worked on creating different logos
Jared | 2018-06-27 | 3 | GUI | GUI Prototype | Researched Googles Material design framework and began implementing a style sheet for the apps design style
Samani | 2018-06-27 | 2 | GUI | GUI Prototype | Worked on creating a send button design
Adam | 2018-06-30 | 2 | Design | Design Document | Design SQA
Adam | 2018-07-02 | 4 | Development | iOS | IOS development - see github
Greg | 2018-07-04 | 10 | Development | iOS Repository | Made core bluetooth work on iOS6
Ben | 2018-07-04 | 10 | Development | Android Repository | Made core bluetooth work on android
Navreet | 2018-07-05 | 1.5 | Development | Android Development | Android Studio Tutorial
Samani | 2018-07-05 | 2 | Development | Android Development | Android Studio Tutorial
Navreet | 2018-07-07 | 3 | SPMP | Software Project Management Plan (SPMP) | Project Organization, Management Objectives, Technical Process
Delina | 2018-07-07 | 1.5 | SPMP | Software Project Management Plan (SPMP) | Management Objectives and Functions
Tiffany | 2018-07-07 | 1.5 | SPMP | Software Project Management Plan (SPMP) | Management Objectives and Functions
Harry | 2018-07-07 | 2 | Development | IOS Development | Implementing settings UI/UX
Tiffany | 2018-07-07 | 2 | Development | IOS Development | Implementing settings UI/UX
Delina | 2018-07-07 | 2 | Development | IOS Development | Implementing settings UI/UX
Adam | 2018-07-08 | 5 | Development | iOS Development | GBluetooth implementation
Yannick | 2018-07-10 | 4 | SQA | Develop start of Automated test Suite | Using appium, but application cannot be launched from the simulator, roadblock on how to run UIAutomator view on physical device
Emily | 2018-07-11 | 3 | Detailed Design | Design Document | Updating subheadings and new content
Rumsha | 2018-07-11 | 2 | Design | Design Analysis | Worked on Module Detailed Design
Harry | 2018-07-11 | 3 | Design | Design Document | Re-organized design doc to include updated headers
Christian | 2018-07-11 | 3 | Design | Design Document | Working on the design documents and views
Cristian | 2018-07-11 | 2 | Design | Design Document | Updating the design document
Jessica | 2018-07-11 | 3 | Design | Design Document | Added the IOS UI descriptions and fields
Farhan | 2018-07-20 | 2 | Design | GUI Prototype | Finalized GUI prototype for couple of screens including bug reporting and minor changes for all other screens
Yannick | 2018-07-20 | 4 | Development | Android Development | Added GUI for navigation menu, as well as included responses for button presses
Cristian | 2018-07-24 | 2 | Development | Android Development | Android Studio Tutorial
Farhan | 2018-07-25 | 2.5 | Development | Android Development | UI for Bug reporting
Adam | 2018-07-27 | 6 | Development | iOS Development | Added support for cross platform and fixed GUI scaling issues
Pranav | 2018-07-29 | 5 | Development | Android Development | Created opening screen branch and pushed onto GIT
Jayanth | 2018-07-31 | 3 | Development | Android Development | Implemented login screen UI
Jared | 2018-07-31 | 4 | Development | Android Development | Curated a meeting to compile everyone Android development screens and work
Jared | 2018-07-31 | 2 | GUI | Android Development | Divided up the work between android devs to give each person a screen to work on
Greg | 2018-07-31 | 3 | Development | iOS Repository | Fixed bugs in screen integrations
Ben | 2018-07-31 | 3 | Development | Android Repository | Fixed bugs in screen integrations
Jared | 2018-08-01 | 2 | Development | Android Development | Researched implementation of Notifications into our Android App
Jared | 2018-08-02 | 1 | Development | Android Development | Worked on my screen for the Android App (Notification settings)
Duncan | 2018-08-08 | 3 | Management | All | Organized team meetings and modified all the documents
Michelle | 2018-08-08 | 2 | SPMP | SPMP Github Doc | Created page and updated
Farhan | 2018-08-08 | 2 | Development | Android Development | Email sending for Bug reporting, unfinished
Malin | 2018-08-08 | 6 | Documentation | Requirements, Analysis and Design Documents | Adding sections that apply class content and delegating others to add descriptions
Jessica | 2018-08-08 | 6 | Documentation | Requirements, Analysis and Design Documents | Adding sections that apply class content and delegating others to add descriptions
Navreet | 2018-08-08 | 3 | SPMP | SPMP Github Doc | Moved SPMP off Google Docs to GitHub
Yannick | 2018-08-08 | 6 | Development | Android Development - Design fixes | Centered Login page, improved overall design of application to closer match Figma
Cristian | 2018-08-08 | 1 | Presentation | Presentation Slide Deck | Helped create the powerpoint for the presentation.
Christian | 2018-08-10 | 2 | Design | IOS Class Module Diagram | Created the IOS class module diagram
Greg | 2018-08-10 | 4 | Development | iOS Repository | Fixing bugs
Yannick | 2018-08-10 | 4 | Development | Android Development - Integrate screens | Integrated the bug report screen, as well as modified it to closer match the original App design
Jared | 2018-08-11 | 2 | Development | Android Development - GUI | Worked on the notifications settings screen adding switches
Yannick | 2018-08-12 | 1 | Development | Android Development - GUI | Improved gui on sandwich/navigation menu to match figma, and highlight text when object is selected
Jared | 2018-08-12 | 3 | Development | Android Development - GUI | Added to the notifications settings screen, adding a chevron to go back and rebase-ing with previous branches
Yannick | 2018-08-12 | 2 | Development | Android Development - Integrate screens | Integrated Jared's screen into navigation menu, covering 3/4 screens required for the sandwich menu
Duncan | 2018-08-13 | 4 | Management | Shout! Presentation | Prepared final presenation slideshow on google slides
Navreet | 2018-08-13 | 3 | SPMP | SPMP | Corrected mistakes based on SQA for GitHub SPMP
Michelle | 2018-08-13 | 4 | SQA | SPMP,Anlysis,Requirements | Fixed documentation and chagnes based on SQA docs
Adam | 2018-08-13 | 5 | Development | iOS Development | Bug fixes and SQA
Duncan | 2018-08-13 | 1 | SQA | SQA logs | Corrected semantic inconcistancies
Ben | 2018-08-14 | 4 | Development | Android Repository | Fixing bugs
Yannick | 2018-08-14 | 5 | Development | Android Repository + development | Integrating 4/4 screens for the sandwich menu, updated functionality, and improved layouts

## SPMP SQA
SPMP
Date SQA'd | SQA'd by | Section | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-06-26 | Emily | 2.1 | 0.1 | Formatting of team divisions | Low | Fixed | Fixed spacing/bold of teams | Navreet | 2018-06-26
2018-06-26 | Rumsha | 4.1 | 0.1 | Add Figma for GUI prototype and change C to Objective C | Moderate | Fixed | Added Figma and Objective C | Navreet | 2018-06-26
2018-06-27 | Duncan | 2.2 | 0.1 | Uncapitalize 'Members' | Low | Fixed | Fixed capitalization error | Michelle | 2018-06-28
2018-06-27 | Duncan | 3.2 | 0.1 | Remove the quotation marks from '"ready"', change '2' to 'two' | Low | Fixed | Fixed both mistakes | Navreet | 2018-06-27
2018-06-28 | Cristian | 1.2 | 0.1 | Implementation and Implementation SQA have an adjusted deadline that is identical to the original deadline | Low | Fixed | No adjusted deadline necessary | Navreet | 2018-06-28
2018-06-28 | Cristian | 1.1 | 0.1 | All words of "Bluetooth low energy" should be captialized | Low | Fixed | Fixed | Michelle | 2018-06-28
2018-08-08 | Rumsha | 2.2 | 0.2 | Error in the Android team text on GitHub | Low | Fixed | Fixed Spelling Error | Michelle | 2018-08-13
2018-08-08 | Tiffany | Heading | 0.2 | Spelling error in heading | Low | Fixed | Fixed Spelling Error | Michelle | 2018-08-13
2018-08-08 | Rumsha | 4.2 | 0.2 | Hyperlink for references does not work | Low | Fixed | Fixed Hyperlinks | Navreet | 2018-08-13
2018-08-08 | Emily | TOC | 0.2 | Hyperlinks to section 1.3, 2.2, 3.1, 3.2, 4.1 | Low | Fixed | Fixed Hyperlinks | Navreet | 2018-08-13
2018-08-08 | Duncan | Heading | 0.2 | Add version number to document | Moderate | Fixed | Added to config | Michelle | 2018-08-13
2018-08-08 | Ranusha | 1.1 | 0.2 | Link 'Bluetooth mesh' instead of just 'mesh' | Low | Fixed | Fixed link | Michelle | 2018-08-13

## Requirements SQA
Requirements
Date SQA'd | SQA'd by | Section | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-05-24 | David Brown | 1.3 | 0.1 | Change last sentence/make it more specific/reword | Low | Fixed | Removed umbrella statement and replaced with more specific sentence | Zak | 2018-06-02
2018-05-24 | David Brown | 1.4 | 0.1 | Remove unused definitions and bold words and add dash to match analysis document | Moderate | Fixed | Corrected | Malin/Samani | 2018-06-02
2018-05-24 | David Brown | 1.5 | 0.1 | Hyperlink IEEE reference | Low | Fixed | Added link | Malin/Samani | 2018-06-02
2018-05-24 | David Brown | 2.2 | 0.1 | Add use case of viewing number of users and their distance + chat cool down in functions paragrah | Moderate | Fixed | Added use case and uploaded new diagram, added sentence to product functions to reflect chat cool down feature | Malin/Samani | 2018-06-02
2018-05-24 | David Brown | 2.1.2 | 0.1 | Edit GUI - view distances addition | Moderate | Fixed | Added a button in chat interface (prototype) to view spanning distance of conversation | Navreet | 2018-06-02
2018-05-24 | David Brown | 2.3 | 0.1 | Specify how there is a learning curve (ex. Shout! will be easy to use for those familiar with iOS and Android) | Low | Fixed | Elaborated on the application ease of usage | Jessica | 2018-06-02
2018-05-24 | David Brown | 2.4 | 0.1 | Reference Apple Human Interface guidelines | Low | Fixed | Added link | Malin/Samani | 2018-06-02
2018-05-24 | David Brown | 2.5 | 0.1 | Link to specific articles | Low | Fixed | Added specific articles | Zak | 2018-06-02
2018-05-24 | David Brown | 3.1/1.4 | 0.1 | Link definitions to words | Moderate | Fixed | Linked definitions to words in article | Malin/Samani | 2018-06-02
2018-05-24 | David Brown | 3.3 | 0.1 | Make it more specific ex. 'how anonymity = security, how data integrity gets checked' (3rd and 4th point), add definitions of 'tech' words ex. token, packet, etc | Moderate | Fixed | Linked definitions on added points, added how data integrity will be managed, added more specific terms and application for security | Pranav | 2018-06-02
2018-05-24 | David Brown | 3.5 | 0.1 | Explain what the modules are or reference them | Moderate | Dismissed | Messages are not stored in these modules, removed section entirely | Malin | 2018-08-08
2018-08-08 | Duncan | 3.3 | 0.2 | Research about Privacy Policies, bluetooth privacy, location privacy (application domain) | Moderate | Fixed | Added information regarding the Terms of Service and the Application Domain under User Characteristics | Jessica | 2018-08-13
2018-08-08 | Duncan |  | 0.2 | Add information about the business model: Android Google Play and iOS store | Moderate | Fixed | Added | Pranav | 2018-08-10
2018-08-08 | Farhan | All | 0.3 | Change all 'app' words to 'application' (needs same standard) | Low | Fixed | No 'app' words | Malin | 2018-08-13
2018-08-08 | Ranusha | All | 0.3 | Create link for requirments doc https://cp317s18.github.io/requirements/ | High | Dismissed | Group decided just to use GitHub link as discussed Facebook chat | Malin | 2018-08-13
2018-08-13 | Cristian | 1.1 | 0.3 | All words of "Bluetooth low energy" should be captialized | Low | Fixed | Fixed | Michelle | 2018-08-13
2018-08-13 | Cristian | 1.3.1 | 0.3 | Comma should be used after "Shout!" and the rest of the sentance should be reworded as it does not flow | Low | Fixed | Fixed | Michelle | 2018-08-13
2018-08-13 | Cristian | 1.3.2 | 0.3 | "Will" incorrectly capitalized | Low | Fixed | Fixed | Michelle | 2018-08-13
2018-08-13 | Cristian | 2.1 | 0.3 | "Androids" should be changed to "Android's" | Low | Fixed | Fixed | Michelle | 2018-08-13
2018-08-13 | Cristian | 2.1.2 | 0.3 | GUI hyperlinks take you to the same heading (do not serve a purpose) | Moderate | Dismissed | Will be edited when Android images added, there as placeholder | Malin | 2018-08-13
2018-08-13 | Cristian | 2.5 | 0.3 | Grammar error: "with Bluetooth Low Energy (BLE) with core specification version 4.0" (double use of with does not sound right) | Low | Fixed | Edited | Malin | 2018-08-13
2018-08-13 | Cristian | 2.5 | 0.3 | ":" missing after "This includes" to represent start of list | Low | Dismissed | Fine as is | Malin | 2018-08-13
2018-08-13 | Cristian | 4.2 | 0.3 | No "." at the end of the sentence | Low | Fixed | Fixed | Michelle | 2018-08-13

## Analysis SQA
Analysis
Date SQA'd | SQA'd by | Section | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-06-02 | Malin | 1.2 | 0.1 | Change wording to suit analysis doc (instead of requirements) | Moderate | Fixed | Fixed wording issue | Andrew | 2018-06-03
2018-06-02 | Jessica | New Section | 0.1 | Consider adding a sequence or state diagrams (refer to "party all" example) | Moderate | Dismissed | Already added | Andrew | 2018-06-02
2018-06-02 | Malin | Title | 0.1 | Change Version to 0.1 at top of document | Low | Fixed | Fixed | Andrew | 2018-06-04
2018-06-02 | Malin | All | 0.1 | Italicize Shout! when referred to in the document | Low | Fixed | Fixed formatting issue | Andrew | 2018-06-04
2018-06-02 | Jessica | 2.4 | 0.1 | Change "colon" to a "dash" after the word Relay | Low | Fixed | Fixed formatting issue | Andrew | 2018-06-04
2018-06-02 | Malin | 2.4 | 0.1 | Make capitalization consistent after the "dash" | Low | Fixed | Fixed formatting issue | Andrew | 2018-06-04
2018-06-02 | Jessica | Header | 0.1 | Remove button for "View on Github" | Low | Dismissed |  | Emily | 2018-06-04
2018-06-02 | Jessica | All | 0.1 | Be consistent with capitalization of "User" or change to lowercase | Low | Fixed | Fixed formatting issue | Andrew | 2018-06-04
2018-06-02 | Andrew | 2.4 | 0.1 | Changed "other others" to "other users" for Send | Low | Fixed | Fixed wording issue | Andrew | 2018-06-04
2018-06-02 | Jessica | 2 | 0.2 | Title in 2.2, 2.3, 2.4 should match the diagram in 2.1 | Low | Fixed | Titles matching | Andrew | 2018-06-04
2018-06-05 | David Brown | 5 | 0.2 | Bluetooth client should be changed from public to getters | Moderate | Fixed | Fixed | Emily/Ben | 2018-06-10
2018-06-05 | David Brown | 5 | 0.2 | Fix attribute3:type in IU Chat Window | Low | Fixed | Fixed | Emily/Ben | 2018-06-10
2018-06-05 | David Brown | 5 | 0.2 | Add inheritance - chat window should talk to parent class, not child | High | Fixed | Fixed | Emily/Ben | 2018-06-10
2018-06-05 | Pranav | 5 | 0.2 | Fix "Message" in receiveMessage() | High | Fixed | Fixed | Emily/Ben | 2018-06-10
2018-06-20 | Rumsha | TOC | 0.2 | Table of Contents is missing "Message Protocol"; last 2 links in ToC not working | High | Fixed | Fixed | Emily | 2018-08-14
2018-06-20 | Michelle | All | 0.3 | Update the version number | Low | Fixed | Updated version number | Emily | 2018-08-14

## Design SQA
Design
Date SQA'd | SQA'd by | Section | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-07-03 | David Brown | 2.1 | 0.1 | Change title of this section / look at other documents | Moderate | Pending | Reworded | Malin | 2018-07-12
2018-07-03 | David Brown | 3.1 | 0.1 | Add image of the protoype from figma | High | Fixed | Added prototype images | Delina | 2018-07-12
2018-07-03 | David Brown | 3.1 | 0.1 | Add the costing strategies for the app (free) | High | Dismissed | To be addressed in requirements doc | Malin | 2018-07-12
2018-07-03 | David Brown | 3.3 | 0.1 | The ledger is no longer updated (grammar) | Moderate | Dismissed | Fixed | Malin | 2018-07-12
2018-07-03 | David Brown | 4.1 | 0.1 | Add in the class diagrams | Low | Fixed | Rearranged details of class diagram | Delina | 2018-07-12
2018-07-03 | David Brown | 4.1 | 0.1 | Make it as connected packages | Moderate | Fixed | Fixed in 0.2 | Malin | 2018-07-12
2018-07-03 | Emily Hryb | 1. and 2. | 0.2 | Make design document more cohesive and organize views | Moderate | Fixed | Changed the content format | Emily | 2018-07-12
2018-07-11 | Samani | 3.4.1 | 0.2 | Change section title to match interface view | Moderate | Fixed | Title changed | Tiffany | 2018-07-12
2018-07-11 | Samani | 3.4.2 | 0.2 | Purpose too vague | Moderate | Fixed | Added additional details and constraints | Christian | 2018-07-12
2018-07-11 | Samani | 3.4.3 | 0.2 | Missing objects in the field table | Moderate | Fixed | Added image object to field table | Tiffany | 2018-07-12
2018-07-11 | Samani | 3.4 | 0.2 | Field names are not consistent | Moderate | Fixed | Changed field names to camelCase | Christian | 2018-07-12
2018-07-11 | Samani | 3.4 | 0.2 | Interface images are blurry | High | Fixed | Reuploaded images with hiugher resolution | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4.2 | 0.2 | Missing objects in the field table | Moderate | Fixed | Added missing button and label objects | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4.2 | 0.2 | Purpose too vague | Moderate | Fixed | Added details about the settings button | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4 | 0.2 | Add gestures column to show sequence of view | Moderate | Fixed | Added to all tables in the section | Tiffany | 2018-07-12
2018-07-12 | Michelle | 3.4 | 0.2 | "Type" names are not consistent | Moderate | Fixed | Change type names to be consistent throughout the document | Delina | 2018-07-12
2018-07-12 | Michelle | 3.4.3 | 0.2 | Purpose does not mention buttons on navigation bar | Moderate | Fixed | Added to the purpose description | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4.4 | 0.2 | Purpose does not mention buttons on navigation bar | Moderate | Fixed | Added to the purpose description | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4.5 | 0.2 | Purpose does not mention buttons on navigation bar | Moderate | Fixed | Added to the purpose description | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4.5 | 0.2 | Missing objects in the field table | Moderate | Fixed | Added reset button object | Jessica | 2018-07-12
2018-07-12 | Michelle | 3.4.6 | 0.2 | Missing objects in the field table | Moderate | Fixed | Added text field object | Jessica | 2018-07-13
2018-07-12 | Michelle | 3.4.6 | 0.2 | Purpose does not mention buttons on navigation bar | Moderate | Fixed | Added Settings View mention | Jessica | 2018-08-08
2018-07-12 | Michelle | 3.4.7 | 0.2 | Purpose does not mention buttons on navigation bar | Moderate | Fixed | Added Settings View mention | Jessica | 2018-08-08
2018-07-12 | Samani | 3 | 0.2 | Add details about colour for objects used | Moderate | Fixed | Added a colour guidelines | Jessica | 2018-07-13
2018-07-12 | Samani | 3.2 | 0.2 | Wrong indentations | Moderate | Fixed | Font of Android added, fixed indents | Jessica | 2018-07-13
2018-07-12 | Michelle | TOC | 0.2 | Titles in Table of Content doesn't match with actual headings | Moderate | Fixed | Titles changed to match | Jessica | 2018-07-13
2018-07-13 | Samani | 1 | 0.2 | iPhone 4S not supported, change to 5 and higher | Low | Fixed | Changed | Malin | 2018-08-13
2018-07-13 | Ranusha | Header | 0.2 | Fix title subheading from "Analysis Document" to "Design Document" | Moderate | Fixed | Fixed | Malin | 2018-08-13
2018-08-08 | Samani | 2.1 | 0.3 | Add description about the language: talk about what language is used and why they were used (portability, cost, compability with existing standards) | High | Fixed | Added a Planned Implementation section to elaborate on the languages | Jessica/Malin | 2018-08-08
2018-08-08 | Andrew | 2.1.2 | 0.3 | Add reasons why Flutter was abandoned (portability) | High | Fixed | Added to the Planned Implementation section | Malin | 2018-08-08
2018-08-08 | Andrew |  | 0.3 | Add Reuse section (code, diagrams) | Moderate | Fixed | Added to the Planned Implementation section | Jessica | 2018-08-08
2018-08-08 | Andrew |  | 0.3 | Add information about the team: ios/android | Low | Fixed | Added to the Planned Implementation section | Jessica | 2018-08-08
2018-08-08 | Samani |  | 0.3 | Add type of integration that will be used to combine the core and design | Moderate | Fixed | Added to the Planned Implementation section | Jessica | 2018-08-08
2018-08-08 | Samani | 3.1.2 | 0.3 | Add class diagram from iOS | High | Fixed | Added to document | Christian | 2018-08-08
2018-08-08 | Adam |  | 0.3 | Core bluetooth module description missing information | Moderate | Fixed | Added missing information | Michelle | 2018-08-08
2018-08-08 | Adam |  | 0.3 | Detailed design module missing method recieve | Moderate | Fixed | Added missing method to design module | Michelle | 2018-08-08
2018-08-08 | Andrew | 6.1 | 0.3 | Mention corrective maintenance in relation to report bugs | Moderate | Fixed | Added a Maintenance section to elaborate on the types of maintances that will be done | Malin | 2018-08-08
2018-08-08 | Andrew | 6.2 | 0.3 | Mention perfective maintenance in relation to future plans and features | Moderate | Fixed | Added to the maintenance section | Jessica/Malin | 2018-08-09
2018-08-08 | Andrew | 6.3 | 0.3 | Mention adaptive maintenance in relation to OS updates | Moderate | Fixed | Added to the maintenance section | Malin | 2018-08-10
2018-08-08 | Andrew | All | 0.3 | Change all 'app' words to 'application' (needs same standard) | Low | Fixed | all words 'application' | Malin | 2018-08-11
2018-12-08 | Samani | TOC | 0.4 | Broken links for section 2 | Moderate | Fixed | Fixed link | Michelle | 2018-08-12
2018-12-08 | Samani | All | 0.4 | Images not appearing | High | Fixed | Changed image links | Michelle | 2018-08-12
2018-12-08 | Jared | 4 | 0.4 | Android prototype needs to be added | High | Fixed | Added | Jessica | 2018-08-14
2018-12-08 | Samani | 4 | 0.4 | <p> in tables appearing | Low | Fixed | Changed to line breaks | Michelle | 2018-08-12
2018-12-08 | Samani | 4 | 0.4 | Tables not consistent with each other | Moderate | Fixed | Fixed table formatting | Jessica | 2018-08-14
13/8/2018 | Navreet | 1 | 0.4 | Incorrect spelling of "Android" | Moderate | Fixed | Corrected spelling | Cristian | 2018-08-14

## UI Prototype SQA
UI Prototype
Date SQA'd | SQA'd by | Section | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-05-24 | Adam | Home View | 0.1 | Add Number of People talking | High | Fixed | Changed to "People Shouting Nearby" | Michelle | 2018-05-24
2018-05-24 | Adam | Home View | 0.1 | Add Hamburger menu | High | Fixed | Added | Michelle | 2018-05-24
2018-05-24 | Adam | Home View | 0.1 | Add Terms of Service link | Moderate | Fixed | Added | Navreet | 2018-05-24
2018-05-24 | Malin | Chat Interface | 0.1 | Add a way to change username | Moderate | Fixed | Added | Navreet | 2018-05-24
2018-05-24 | Adam | Chat Interface | 0.1 | Add a way to share location | Low | Fixed | Added | Michelle | 2018-05-24
2018-05-24 | Farhan | Chat Interface | 0.1 | Add a scroll bar | Low | Fixed | Added | Navreet | 2018-05-24
2018-05-29 | Malin | Home View | 0.2 | Change the colour theme to match colour palette | High | Fixed | Changed the colours and removed the circle | Navreet | 2018-05-30
2018-05-29 | Malin | Chat Interface | 0.2 | Change the colour theme to match colour palette | High | Fixed | Changed the colours | Michelle | 2018-05-30
2018-05-29 | Michelle | Home View | 0.2 | Separate iOS designs from Andriod designs | High | Fixed | Separated into different drafts | Jessica | 2018-05-30
2018-05-29 | Michelle | Home View | 0.2 | Add Logo in the app | High | Fixed | Added | Jessica | 2018-05-30
2018-05-29 | Michelle | Home View | 0.2 | Change button into rounded ones | Low | Fixed | Changed | Jessica | 2018-05-30
2018-06-12 | Michelle | Home View | 0.2 | Add a shadow to the buttons | Low | Fixed | Added | Jessica | 2018-06-15
2018-06-12 | Michelle | Home View | 0.2 | Change iOS font to default font | High | Fixed | Changed | Jessica | 2018-06-15
2018-06-12 | Navreet | Chat Interface | 0.2 | Remove additional features to fit with constraints | Moderate | Fixed | Removed | Jared | 2018-06-18
2018-06-12 | Navreet | Chat Interface | 0.2 | Change settings notification to standardize | Low | Fixed | Changed | Jared | 2018-06-18
2018-06-20 | Navreet | Chat Interface | 0.2 | Change send button to a symbol | Moderate | Fixed | Changed | Jared | 2018-06-21
2018-06-20 | Navreet | Chat Interface | 0.2 | Remove border around text field for clean look | Low | Fixed | Removed | Jared | 2018-06-21
2018-06-20 | Navreet | Settings | 0.2 | Change the padding on the settings notifcation | Moderate | Fixed | Changed | Jessica | 2018-06-21
2018-06-20 | Navreet | Settings | 0.2 | Change the accent for clicking actions | Low | Fixed | Changed | Jared | 2018-06-21
2018-06-20 | Navreet | General | 0.3 | Change iOS menu bar to button instead of hamburger menu | High | Fixed | Changed | Jessica | 2018-06-21
2018-06-22 | Navreet | Settings | 0.3 | Remove Change Username option | High | Fixed | Removed | Jessica | 2018-06-30
2018-06-24 | Michelle | Settings | 0.3 | Remove Send button, already in navigation | High | Fixed | Removed | Jessica | 2018-06-30
2018-06-25 | Michelle | Settings | 0.3 | Titles don't align for all the settings pages | High | Fixed | Adjusted the aligments | Jared | 2018-06-30
2018-07-10 | Malin | Home View | 0.3 | Remove line for username change | Low | Fixed | Removed | Jared | 2018-07-14
2018-07-11 | Michelle | Settings | 0.3 | Different fonts are being used in the settings page | Moderate | Fixed | Change all fonts to SF Pro and Roboto for Android | Jessica | 2018-07-14
2018-07-11 | Michelle | Settings | 0.3 | Spelling error on Notification: "notificaton" | High | Fixed | Fixed | Jessica | 2018-07-14
2018-07-11 | Michelle | Settings | 0.3 | Spelling error on Report Bug: "probelm" | High | Fixed | Fixed | Jessica | 2018-07-14
2018-07-11 | Navreet | Settings | 0.3 | Change Back on Settings to "Home" | Low | Fixed | Changed | Jared | 2018-07-14
2018-07-11 | Navreet | Settings | 0.3 | Change Back on Notification to "Settings" | Low | Fixed | Changed | Jared | 2018-07-14
2018-07-11 | Navreet | Settings | 0.3 | Change Back on Report to "Settings" | Moderate | Fixed | Changed | Jared | 2018-07-14
2018-07-11 | Navreet | All | 0.3 | Captialize the words on buttons | Low | Fixed | Fixed | Jessica | 2018-07-15
2018-07-15 | Navreet | Home View | 0.4 | Change settings symbol to a different color (fades into background) | High | Fixed | Changed | Jessica | 2018-07-15
2018-07-15 | Navreet | Home View | 0.4 | Change the number to different colour to make it stand out | Low | Fixed | Changed | Jessica | 2018-07-15
2018-07-15 | Michelle | Home View | 0.4 | The logo doesn't stand out | High | Fixed | Border added to the logo | Jared | 2018-07-15
2018-07-15 | Adam | Bluetooth | 0.4 | Change the description, make it consise | Moderate | Fixed | Changed | Jessica | 2018-07-15
2018-07-15 | Michelle | Bluetooth | 0.4 | Change the symbol to a transparent image | High | Fixed | Changed | Jared | 2018-07-15
2018-07-15 | Michelle | Bluetooth | 0.4 | Change the spacing between the description and image | Low | Fixed | Changed | Jared | 2018-07-15

## Android SQA
Android Development
Date SQA'd | SQA'd by | Section | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-07-04 | Yannick |  |  | Messages sending inconsistently | High | Fixed | Updated Bluetooth Client Class | Ben | 2018-07-05
2018-07-08 | Pranav |  |  | Bluetooth not automatically turned on | High | Fixed | Changed bluetooth permissions | Ben | 2018-07-10
2018-07-09 | Farhan |  |  | Keyboard not disappearing when sending message | High | Fixed | Updated Main Activity | Ben | 2018-07-10
2018-07-10 | Ben |  |  | No app icon | Low | Fixed | Added app icon | Pranav | 2018-07-11
2018-07-15 | Yannick |  |  | Cannot return to main screen | High | Fixed | Added button functionality | Pranav | 2018-07-29
2018-07-20 | Farhan |  |  | Font too big in chat screen | Low | Fixed | Reduced font | Jayanth | 2018-07-30
2018-07-20 | Alex | navigation_menu |  | Need navigation menu | High | Fixed | Updated features branch | Jayanth | 2018-07-30
2018-07-25 | Jared | navigation_menu |  | Remove hard coded colors | Moderate | Fixed | Added into colours file | Yannick | 2018-07-31
2018-07-25 | Jared | navigation_menu |  | Include structure for each action | Moderate | Fixed | Fixed file ordering | Yannick | 2018-07-31
2018-07-25 | Jayanth |  |  | App crashing when trasitioning between screens | High | Fixed | Moved to alert dialogs | Ben | 2018-07-31
2018-07-28 | Yannick |  |  | Cross platform failing connections | High | Fixed | Changed bluetooth client class | Ben | 2018-07-31
2018-07-30 | Pranav |  |  | Change username not working | Low | Fixed | Updated main activity class | Ben | 2018-07-31
2018-07-30 | Farhan |  |  | No push notifications | Low | Fixed | Added push notifications | Ben | 2018-07-31
2018-07-30 | Yannick |  |  | Many messages crashes app | High | Fixed | Bluetooth client change | Jared | 2018-07-31
2018-07-30 | Ben |  |  | Menu screen too small | Moderate | Fixed | Changed layout to a Horizontal layout | Yannick | 2018-07-31
2018-07-30 | Ben |  |  | Need sidebar menu | High | Fixed | Added sidebar | Yannick | 2018-07-31
2018-07-30 | Emily |  |  | Change size text on main screen | Moderate | Fixed | Added constaints to align elements | Jayanth | 2018-07-31
2018-07-30 | Jared |  |  | Button not rounded | Low | Fixed | Fixed button | Alex | 2018-07-31
2018-07-30 | Jared |  |  | Colours do not match design | Low | Fixed | Changed colours | Alex | 2018-07-31
2018-07-30 | Jared | bug_report2 |  | Need Bug report layout | High | Fixed | Added | Farhan | 2018-08-13
2018-07-30 | Ben | bug_report2 |  | Add textbox for bugs | Moderate | Fixed | Added textbox | Farhan | 2018-08-13
2018-07-30 | Yannick | bug_report2 |  | Remove hard coded strings | Moderate | Fixed | Hardcoded strings removed | Farhan | 2018-08-13
2018-07-30 | Ben | bug_report2 |  | Add button to send report | High | Fixed | Button added | Farhan | 2018-08-13
2018-07-30 | Pranav | bug_report2 |  | Bug report error | High | Fixed | Error message fixed | Farhan | 2018-08-13
2018-08-01 | Pranav |  |  | Need settings screen | Moderate | Fixed | Added screen | Jared | 2018-08-13
2018-08-01 | Jayanth |  |  | Toggle buttons in setting screen not working properly | Moderate | Fixed | Working properly | Jared | 2018-08-13
2018-08-01 | Yannick |  |  | About screen spelling error | Low | Fixed | Fixed spelling | Emily | 2018-08-13
2018-08-01 | Yannick |  |  | Terms of service font too big | Low | Fixed | Changed font sized, reduced font | Emily | 2018-08-13
2018-08-01 | Yannick |  |  | About screen scaling too big | Low | Fixed | Changed the layout | Emily | 2018-08-13
2018-08-08 | Farhan | bug_report3 |  | Button does not send email | Moderate | Dismissed | End of project | Yannick | 2018-08-14
2018-08-08 | Farhan |  |  | Link bug report to menu | High | Dismissed | End of project | Yannick | 2018-08-14

## iOS SQA
iOS Development
Date SQA'd | SQA'd by | Version | Correction to be Made | Priority | Status | Action Taken | Corrected by | Date Fixed
2018-07-06 | Greg | 0.1.0 | Messages failing to transmit | High | Fixed | Added module to retry | Adam | 2018-07-06
2018-07-06 | Greg | 0.1.1 | Main view controller scaling incorrect | Moderate | Fixed | Fixed by adding constraints | Adam | 2018-07-06
2018-07-06 | Greg | 0.1.1 | Intermittent connection issues | High | Fixed | Issue with bluetooth module - reset to default seems to fix | Adam | 2018-07-06
2018-07-07 | Delina | 0.1.1 | Failing animations on main chat screen | Low | Fixed | Fixed and merged animation changes | Greg | 2018-07-07
2018-07-07 | Christian | 0.1.2 | Launchscreen scaling issue | Low | Fixed | Minor issue with launchscreen.swift | Adam | 2018-07-07
2018-07-07 | Christian | 0.1.2 | Add functionality for viewing number of connections | Moderate | Fixed | Functionality added | Adam | 2018-07-07
2018-07-07 | Adam | 0.1.2 | Number of connections fails to show | Low | Fixed | Connected to main app delegate class | Greg | 2018-07-07
2018-07-10 | Harry | 0.1.3 | Cross platform failing connections | High | Fixed | Shifted main connection module to app delegate | Adam | 2018-07-14
2018-07-10 | Harry | 0.1.4 | Intermittent connection issues | Moderate | Fixed | API keys not matching - fixed | Greg | 2018-07-14
2018-07-10 | Adam | 0.1.5 | Listeners duplicated - causes intermittent dropped connections | Moderate | Fixed | Added remove listener function core | Greg | 2018-07-14
2018-07-10 | Delina | 0.1.5 | iOS crashing due to high volume of messages | Moderate | Fixed | Added core data support | Greg | 2018-07-14
2018-07-11 | Tiffany | 0.1.6 | Text not wrapping properly | Moderate | Fixed | Text now wraps around username - multiline support | Adam | 2018-07-14
2018-07-11 | Alex | 0.1.7 | Confusing UI for navigating | Low | Fixed | Changed direction of leaving chat | Adam | 2018-07-15
2018-07-13 | Jessica | 0.2.0 | Improper frame size for messages | High | Fixed | Intermittent issue - updated constraints seems to prevent] | Greg | 2018-07-16
2018-07-13 | Jessica | 0.2.0 | Finalized UI not scaling properly | Low | Fixed | Fixed constraints | Malin | 2018-07-18
2018-07-25 | Delina | 0.2.0 | New UI breaks backend for sending messages | High | Fixed | Endpoints improperly connected - fixed | Malin | 2018-07-29
2018-07-25 | Delina | 0.2.0 | Confusing naming scheme for new/old UI | Low | Fixed | Went through and cleaned up issue | Jessica | 2018-07-29
2018-07-26 | Harry | 0.2.2 | Menu items stacking instead of displaying properly | Moderate | Fixed | Fixed issue where menu items stacking | Jessica | 2018-07-30
2018-08-01 | Christian | 0.2.3 | Layout of code is confusing in MainViewController | Moderate | Fixed | Reordered and itemized for future edits | Malin | 2018-08-08
2018-08-09 | Tiffany | 0.2.3 | iOS and Android app cross functionality no longer works | High | Fixed | Rematched API keys and call | Adam | 2018-08-10
2018-08-09 | Tiffany | 0.2.3 | 'About Shout!' page not complete | Moderate | Dismissed | End of project | Malin | 2018-08-13

## Members SQA Status
SQA
Name | Documents SQAed
Greg | Requirements
Adam | Design
Alex | Design
Andrew | Design
Benjamin | Development
Christian | Analysis
Cristian | Requirements
Delina | Requirements
Duncan | Requirements, SPMP
Emily | SPMP
Farhan | Requirements
Harry | Analysis
Jared | Development
Jayanth | Requirements
Jessica | Analysis
Zakaria | Requirements
Malin | Analysis
Michael | Requirements
Michelle | Analysis
Navreet | Analysis
Pranav | Analysis
Ranusha | Design, Requirementsm, SPMP
Rumsha | Analysis
Samani | Design
Tiffany | SPMP
Yannick | Development
Zakaria | Analysis
Rumsha | SPMP